## HR
Military Land Management System (MLMS)
SL | Name | Role | Man-Months
1 | Md. Reazul Islam Polash | Project Manager | 6
2 | M. Nayem Abdullah | Business Analyst | 4
3 | Md. Moinul Islam | Solution Architect | 4
4 | Bijoy Lal Dewanjee | Senior Software Engineer | 6
5 | Md. Mamun Miah | Software Engineer | 6
6 | Mirbahar Nurul Amin | Software Engineer
7 | Asif Atick | Data Scientist
8 | Samiul Abid Chowdhury | Data Engineer | 6
9 | Md. Tariqul Islam | Data Engineer
10 | Ziaur Rahman | UI Engineer
11 | Forhadul Islam | Infrastructure Expert
12 | Maksudur Rahman | Document Writer
13 | Marufuzzaman Maruf | QA Engineer | 6
14 | Md. Mehedi Hasan | Software Support & Maintenance Engineer | 6
15 | Nafiz Imtiaz | Software Support & Maintenance Engineer
16 | Md. Moniruzzaman Miah | Visualization Expert

## 5A5 Work schedule1
|  | Development Phase in day | [11 empty] | Suport and maintenance
Sl. No. | Phase and Description | [12 empty] | Months
|  | Day 1 | Day 2-3 | Day 4-5 | Day 6-10 | Day 11-12 | Day 13-15 | Day 16-60 | Day 61-90 | Day 91-120 | Day 121-125 | Day 126-130 | 12 | 13 | 14 | 15
Phase 1: Inception Report (5 days)
1 | Review project scope and gather information
2 | Write and review the Inception Report
3 | Finalize and submit the Inception Report
5 | High level design development
6 | Submission of Project Management Plan
Phase 2: Software Requirement Specification (SRS) (15 days)
7 | Gather requirements and conduct interviews with stakeholders
8 | Write and review the SRS
9 | Finalize and submit the SRS
8 | Structural Layout Development and design of the system
9 | Review Existing existing database and software
10 | Detail Test Plan & Review
11 | System architecture assessment and provide recommendations
12 | Coding & Review
13 | Established Cloud-based multiple dashboards under one umbrella
14 | Designing the Database of the Software
15 | Integration of system with 3 type user Dashboard (Strategic dashboards, Analytical dashboards, Operational dashboards)
16 | Security Standard Implementation for the System
17 | Delivery of the First iteration
18 | Integration
Phase 3: Software Development (120 days)
19 | Develop and test software features
18 | Continue development and testing
Finalize development and prepare for testing
19 | Data Warehouse
20 | Sourcing, Acquisition, Clean-up, and Transformation Tools (ETl)
21 | Collection of Matadata, Data Marts
22 | Data Pipeline from source to Dashboard.
Phase 4: Testing (10 days)
23 | Conduct UAT and vulnerabilityTesting
24 | Product design review based on Tests and user feedback
25 | Feedback Accommodation
26 | Migration of legacy data
27 | Signing of User Acceptance Report
28 | Training
29 | Go live
Phase 5: Support and Maintenance
30 | Support & Maintenance

## 5A6 Team Composition
Form 5A6 Team Composition and Task Assignments
SL No | Person | Firm | Area of Expertise | Position Assigned | Task Assigned
1 | Md. Riazul Islam Polash | Devnet | • Strong connection with major stakeholders like local chambers, associations, government ministries, Proven Project Delivery and Management experience specific to Bangladesh government, • Association of Chartered Certified Accountants (ACCA), UK, London. • 11 years of experience in large scale ICT implementation projects • ACMP Certified-Ref. MDP/ACMP 4.0-B7.190 | Project Manager | The Project Manager is responsible for the day-to-day operational management of the project, including developing and overseeing work and preparation of project progress reports. He is responsible for regular reporting to the client. The chosen candidate is responsible for overseeing all technical aspects of the project implementation including analyse the user requirements, develop software design, choose the right technical solution as well as oversee the right implementation to ensure sustainability. Responsible for technical, financial and administrative management of the assignment. Supervise development & testing of the application software, Supervise data migration, design & development; Monitor application software development, Supervise Database Design,HW setup, web application development; Organize & prepare/consolidate inception report, progress reports, manuals, training materials, etc.
2 | M. Nayem Abdullah | Devnet | • Evaluating business processes • Requirement analysis • Technology analysis • Application Architecture Analysis • Application Architecture Design | Business Anakyst | • Evaluating business processes, anticipating requirements, uncovering areas for improvement, and developing and implementing solutions. • Leading ongoing reviews of business processes and developing optimi-zation strategies. • Staying up-to-date on the latest process and IT advancements to auto-mate and modernize systems. • Conducting meetings and presentations to share ideas and findings. • Performing requirements analysis. • Documenting and communicating the results of your efforts. • Effectively communicating your insights and plans to cross-functional team members and management. • Gathering critical information from meetings with various stakeholders and producing useful reports. • Working closely with clients, technicians, and managerial staff. • Providing leadership, training, coaching, and guidance to junior staff.
3 | Md. Moinul Islam | Devnet | • Application Architecture Analysis • Application Architecture Design • ICT System requirements Collection • ICT System requirements analysis • Interface design and implementation • OOP design and implementation • UML and technical documentation • CTI Application Design and implementation • Client requirements and actual business proposition plan | Solution Architect | The system analyst is expected to analyse the user requirements through meetings and discussion session with the targeted beneficiaries. After finalizing the primary draft of User Requirement Specification through vetting with the users, the System Analyst will prepare the Software Design Document in consultation with the Team leader/Project Manager and share the document with QA specialist. Specifically, the System Analyst will- • Design the architecture for system integration as required • Prepare plans for optimal data storage and retrieval procedures • Prepare plans for data standardization • Prepare SRS • Prepare other technical documentation as per project requirement. • ICT System requirements Collection • ICT System requirements analysis • Interface design and implementation • OOP design and implementation • UML and technical documentation • CTI Application Design and implementation • Client requirements and actual business proposition plan
4 | Bijoy Lal Dewanjee |  | • Team management • Programming, coding • Customization • Writing and implementing efficient code • Developing quality assurance procedures • Deploying software tools, processes and metrics | Senior Software Engineer | • Responsible for developing software coding as per design for PC & Mobile • The Software Developers are expected to code the software. This includes design, develop, and modify the modules with arranging the needed functionalities accordingly. The database backend is also expected to be developed by this team, including adding and modifying the structure, the stored procedures (if any), • Coordinate with the Technical lead on current programming tasks • Develop mobile app and web application • Collaborate with other programmers to design and implement features • Quickly produce well organized, optimized and documented source code • Create and document software tools required by other developers and stake holders. • Debug existing source code and polish feature sets • Contribute to technical design documentation
5 | Md. Mamun Miah | Devnet | • Team management • Programming, coding • Customization • Writing and implementing efficient code • Developing quality assurance procedures • Deploying software tools, processes and metrics | Software Engineer | • Responsible for developing software coding as per design for PC & Mobile • The Software Developers are expected to code the software. This includes design, develop, and modify the modules with arranging the needed functionalities accordingly. The database backend is also expected to be developed by this team, including adding and modifying the structure, the stored procedures (if any), • Coordinate with the Technical lead on current programming tasks • Develop mobile app and web application • Collaborate with other programmers to design and implement features • Quickly produce well organized, optimized and documented source code • Create and document software tools required by other developers and stake holders. • Debug existing source code and polish feature sets • Contribute to technical design documentation
6 | Mirbahar Nurul Amin | Devnet |  Programming  Writing and implementing efficient code  Customization | Software Engineer | • Responsible for developing software coding as per design • The Software Developers are expected to code the software. • Coordinate with the sr. developers on current programming tasks • Collaborate with other developers to design and implement features • Quickly produce well organized, optimized and documented source code • Create and document software tools required by other developers and stake holders. • Debug existing source code and polish feature sets • Contribute to technical design documentation
7 | Asif Atick | Devnet | • Data collecting & processing • Process automation • Business Inteligent • Machine Learning • Deep Learning OCR and ICR, NLP, .Net developer, Python | Data Scientist | • Data mining or extracting usable data from valuable data sources • Using machine learning tools to select features, create and optimize classifiers • Statistics and probability cast on data via Deep Learning • Carrying out pre-processing of structured and unstructured data • Enhancing data collection procedures to include all relevant information for developing analytic systems • Processing, cleansing, and validating the integrity of data to be used for analysis • Analyzing large amounts of information to find patterns and solutions • Developing prediction systems and machine learning algorithms • Presenting results in a clear manner • Propose solutions and strategies to tackle business challenges • Collaborate with Business and IT teams
8 | Samiul Abid Chowdhury | Devnet | • Data collecting & processing • Process automation • Business Inteligent • Machine Learning • Deep Learning OCR and ICR, NLP, .Net developer, Python | Data Engineer | • Data mining or extracting usable data from valuable data sources • Using machine learning tools to select features, create and optimize classifiers • Statistics and probability cast on data via Deep Learning • Carrying out pre-processing of structured and unstructured data • Enhancing data collection procedures to include all relevant information for developing analytic systems • Processing, cleansing, and validating the integrity of data to be used for analysis • Analyzing large amounts of information to find patterns and solutions • Developing prediction systems and machine learning algorithms • Presenting results in a clear manner • Propose solutions and strategies to tackle business challenges • Collaborate with Business and IT teams
9 | Md. Tariqul Islam | Devnet | • Data collecting & processing • Process automation • Business Inteligent • Machine Learning • Deep Learning OCR and ICR, NLP, .Net developer, Python | Data Engineer | The QA Engineer will act as the person responsible for ensuring the final product that reaches the client (Software, documentation and training) are up to the acceptable mark as decided earlier by leading the QA team. Specifically he will – • Create test plans, requirements, scenarios and test data for use during testing. • Develop test cases and prioritize testing activities. • Execute all the test case and report defects, define severity and priority for each defect. • Carry out regression testing every time when changes are made to the code to fix defect • Verify and approve the test cases • Prepare the combined test report and communicate with the developer’s team • Act as a release manager for issuing the product to the client
10 | Ziaur Rahman | Devnet | Design User Interface | UI Designer | • UI Design & Implenting •Setting up, developing and maintaining computer networks within the project site. • maintenance of computer networks, hardware, software, and other related systems • Maximizing network performance through ongoing monitoring and troubleshooting • Performing disaster recovery operations • Protecting data, software, and hardware from attacks, and replacing faulty network hardware components when necessary.
11 | Forhadul Islam | Devnet | • Plan & Implement Software Design • Programming • Hardware maintenance and Plan | Infrastructure Expert |  Assist in plan design, hardware implementation, software, network and telephony capabilities;  Diagnose and resolve hardware, software, network and telephony issues;  Assist in developing operating, installation, and upgrade procedures for communication systems, hardware, network, security, storage and software;  Assist in documenting current hardware and network environments, including servers, PCs, IT security and network systems, videoconferencing and telephony;  Perform Help Desk and desktop support activities, as needed;  Research, analyses, and assist in developing documentation and new processes and procedures collaboratively with Director of Infrastructure
12 | Maksudur Rahman | Devnet | •Certified Scrum Product Owner, Scrum Alliance, Certificate ID: 000589827, June 2020 •Project Management Professional (35 PDU) Day Spring Dhaka, January 2018 •Certified Scrum Master, Scrum Alliance: Certificate ID: 589827, November 2016 •Agile Inception –In-depth Exposure to Agile, BD Jobs, Dhaka, April 2014 | Document Expert |  Work with internal teams to obtain an in-depth understanding of the product and the documentation requirements  Produce high-quality documentation that meets applicable standards and is appropriate for its intended audience  Write easy-to-understand user interface text, online help and developer guides  Create tutorials to help end-users use a variety of applications  Analyze existing and potential content, focusing on reuse and single-sourcing opportunities  Create and maintain the information architecture
13 | Marufuzzaman Maruf | Devnet |  conducting software testing  creating test-product documentation | QA Engineer | The QA Engineer will act as the person responsible for ensuring the final product that reaches the client (Software, documentation and training) are up to the acceptable mark as decided earlier by leading the QA team. Specifically he will – • Create test plans, requirements, scenarios and test data for use during testing. • Develop test cases and prioritize testing activities. • Execute all the test case and report defects, define severity and priority for each defect. • Carry out regression testing every time when changes are made to the code to fix defect • Verify and approve the test cases • Prepare the combined test report and communicate with the developer’s team • Act as a release manager for issuing the product to the client
14 | Md. Mehedi Hasan | Devnet | • Networking • Device management • Hardware maintenance and troubleshooting | Software Maintenance & Support Engineer | • Setting up, developing and maintaining computer networks within the project site. • maintenance of computer networks, hardware, software, and other related systems • Maximizing network performance through ongoing monitoring and troubleshooting • Performing disaster recovery operations • Protecting data, software, and hardware from attacks, and replacing faulty network hardware components when necessary.
15 | Nafiz Imtiaz | Devnet | • Networking • Device management • Hardware maintenance and troubleshooting | Software Maintenance & Support Engineer | • Setting up, developing and maintaining computer networks within the project site. • maintenance of computer networks, hardware, software, and other related systems • Maximizing network performance through ongoing monitoring and troubleshooting • Performing disaster recovery operations • Protecting data, software, and hardware from attacks, and replacing faulty network hardware components when necessary.
16 | Md. Moniruzzaman Miah | Devnet | • Software development • Database design and development • Integration • Data security | Visualization Expert | • Responsibility for the evaluation of database software purchases • Supervision of modifications to any existing database software to meet the needs of their employer • Responsibility for maintaining the integrity and performance of company databases • Must guarantee that data is stored securely and optimally • Informing end users of changes in databases and train them to utilize systems • Ensuring the security of company data

## 5A7 Staffing Schedule
No. | Name | Staff Month input by month in Development phase | [11 empty] | Staff month during operation and maintenance |  |  | Total Staff Month Input
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Home | Field | Total
1 | Md. Reazul Islam Polash | [17 empty] | 12 | 350000 | 4200000 | 6 |  | 1 | Project Manager
[21 empty] | 0 | 4 | Prof. Dr. Dewan Md. Farid | 2 | System Analyst
2 | M. Nayem Abdullah | [17 empty] | 6 | 300000 | 1800000 | 4 | Hasan Sarwar | 3 | Team Leader
[21 empty] | 0 | 6 | Md. Moinul Islam | 4 | Business Process Specialist
3 | Md. Moinul Islam | [17 empty] | 6 | 300000 | 1800000 | 6 | Md. Reazul Islam Polash | 5 | Senior Software Engineer/Programmer
[21 empty] | 0 | 6 | Md. Moniruzzaman Miah | 6 | Senior Software Engineer/Programmer
4 | Bijoy Lal Dewanjee | [17 empty] | 12 | 300000 | 3600000 | 6 | Bijoy Lal Dewanjee | 7 | Senior Software Engineer/Programmer
[21 empty] | 0 | 6 | M. Nayem Abdullah | 8 | Software Engineer/Programmer
5 | Md. Mamun Miah | [17 empty] | 4 | 250000 | 1000000 | 6 | Md. Asif Atick | 9 | Software Engineer/Programmer
[21 empty] | 0 | 1 | Harun or Rashid | 10 | Software Engineer/Programmer
6 | Mirbahar Nurul Amin | [17 empty] | 4 | 250000 | 1000000 | 3 | Md. Mamun Miah | 11 | Software Engineer/Programmer
[21 empty] | 0 | 6 | Sohag Hossain | 12 | Software Engineer/Programmer
7 | Asif Atick | [17 empty] | 4 | 250000 | 1000000 | 6 | Mirbahar Nurul Amin | 13 | Lead Software Quality Assurance and Testing Engineer (SQA)
[21 empty] | 0 | 6 | Md. Sohel Rana | 14 | Software Quality Assurance and Testing Engineer (SQA)
8 | Samiul Abid Chowdhury | [17 empty] | 3 | 200000 | 600000 | 6 | Samiul Abid Chowdhury | 15 | Software Quality Assurance and Testing Engineer (SQA)
[21 empty] | 0 | 3 | Md. Tariqul Islam | 16 | Software Quality Assurance and Testing Engineer (SQA)
9 | Md. Tariqul Islam | [17 empty] | 3 | 200000 | 600000 | 2 | Forhadul Islam | 17 | Software Quality Assurance and Testing Engineer (SQA)
[21 empty] | 0 | 12 | Nafiz Imtiaz | 18 | System Networking Engineer
10 | Ziaur Rahman | [17 empty] | 3 | 200000 | 600000 |  |  | 19 | System Networking Engineer
[21 empty] | 0 |  |  | 20 | System Networking Engineer
11 | Forhadul Islam | [17 empty] | 3 | 200000 | 600000 |  |  | 21 | System Operations and Maintenance Engineer
[21 empty] | 0 |  |  | 22 | System Operations and Maintenance Engineer
12 | Maksudur Rahman | [17 empty] | 4 | 200000 | 800000 |  |  | 23 | System Operations and Maintenance Engineer
[21 empty] | 0 |  |  | 24 | System Operations and Maintenance Engineer
13 | Marufuzzaman Maruf | [17 empty] | 3 | 200000 | 600000 |  |  | 25 | Data Science Specialist
[21 empty] | 0 |  |  | 26 | Data Science Specialist
14 | Md. Mehedi Hasan | [17 empty] | 6 | 150000 | 900000 |  |  | 27 | Trainer
[21 empty] | 0 |  |  | 28 | Trainer
15 | Nafiz Imtiaz | [17 empty] | 3 | 150000 | 450000 |  |  | 29
[21 empty] | 0 |  |  | 30
16 | Md. Moniruzzaman Miah | [17 empty] | 9 | 150000 | 1350000 |  |  | 31
[21 empty] | 0 |  |  | 32
| Total | [17 empty] | 85 |  | 20900000

## 5B3 Staff Remuneration
Form 5B3 Breakdown of Staff Remuneration
S.L. | Name1 | Position2 | Staff-month Rate3 | Input3 | [Indicate Sub Cost for each staff] 4
(Staff-months)
Staff
1 | Md. Maksudur Rahman | Project Manager | 300000 | 9 | 2700000
0
2 | Md. Moinul Islam | System Analyst | 300000 | 9 | 2700000
|  | Business Process Specialist |  |  | 0
3 | Md. Reazul Islam Polash | Team Leader | 350000 | 9 | 3150000
0
4 | M. Nayem Abdullah | Business Process Specialist | 250000 | 9 | 2250000
0
5 | Mohammad Syful Islam Noman | Senior Software Engineer | 250000 | 9 | 2250000
0
6 | Md. Mamun Miah | Senior Software Engineer | 250000 | 9 | 2250000
0
7 | Bijoy Lal Dewanjee | Senior Software Engineer | 250000 | 5 | 1250000
0
8 | Sohag Hossain | Software Engineer | 200000 | 8 | 1600000
0
9 | Mirbahar Nurul Amin | Software Engineer | 200000 | 8 | 1600000
0
10 | Ziaur Rahman | Software Engineer | 200000 | 8 | 1600000
0
11 | Samiul Abid Chowdhury | Software Engineer | 200000 | 8 | 1600000
0
12 | Md.Majharul Islam | Software Engineer | 200000 | 8 | 1600000
0
13 | Md. Moniruzzaman Miah | Lead Software Quality Assurance and Testing Engineer | 150000 | 8 | 1200000
0
14 | Harun or Rashid | Software Quality Assurance and Testing Engineer | 120000 | 6 | 720000
0
15 | Marufuzzaman Maruf | Software Quality Assurance and Testing Engineer | 120000 | 6 | 720000
0
16 | Md. Tariqul Islam | Software Quality Assurance and Testing Engineer | 120000 | 6 | 720000
0
17 | Md. Sohel Rana | Software Quality Assurance and Testing Engineer | 120000 | 6 | 720000
0
18 | Forhadul Islam | System Networking Engineer | 120000 | 6 | 720000
0
19 | Md. Obaidul Haque Sarker | System Networking Engineer | 120000 | 3 | 360000
0
20 | Jubair Al Ansary | System Networking Engineer | 120000 | 3 | 360000
0
21 | Roni Kumar Saha | Data Science Specialist | 250000 | 4 | 1000000
0
22 | Asif Atick | Data Science Specialist | 250000 | 4 | 1000000
0
23 | Md. Nazmul Hasan | Trainer | 120000 | 1 | 120000
0
24 | Md. Zahirul Islam | Trainer | 120000 | 3 | 360000
0
32550000

## 5B5 Staff Remuneration O&M
Form 5B5: Breakdown of operation & maintenance Expenses (Lump-Sum)
S.L. | Name1 | Position2 | Staff-month Rate3 | Input3 | [Indicate Sub Cost for each staff] 4
(Staff-months)
Staff
1 | Bijoy Lal Dewanjee | Senior Software Engineer | 250000 | 4 | 1000000
0
2 | Samiul Abid Chowdhury | Software Engineer | 200000 | 12 | 2400000
0
3 | Nafiz Imtiaz | System Operations and Maintenance Engineer | 100000 | 12 | 1200000 | 12 | 1200000
[5 empty] | 0 |  | 0
4 | Md. Mehedi Hasan | System Operations and Maintenance Engineer | 100000 | 12 | 1200000 | 12 | 1200000
[5 empty] | 0 |  | 0
5 | Shahriar Rahman | System Operations and Maintenance Engineer | 100000 | 12 | 1200000 | 12 | 1200000
[5 empty] | 0 |  | 0
6 | Abdul Kaiyum | System Operations and Maintenance Engineer | 100000 | 12 | 1200000 | 12 | 1200000
0
8200000
40750000

## Reimbursible
N° | Description1 | Unit | Unit Cost | Quantity | Amount
1 | Per diem allowances | Day | 14000 | 180 | 2520000
2 | Travel expenses | Trip | 1500 | 180 | 270000
3 | Communication costs | minute | 3 | 20000 | 60000
4 | Drafting, reproduction of reports | pages | 15 | 10000 | 150000
5 | Office rent | Months | 9 | 106800 | 961200
6 | Use of computers and other equipment | lumpsum |  |  | 1344000
7 | Training | lumpsum |  |  | 500000
5805200
|  |  |  | HR | 40750000
|  |  |  | Reimbursible | 5805200
|  |  |  | Sub total | 46555200 | 9311040
|  |  |  | Vat @ 5% | 2327760
Tax @ 5%
48882960

## 5B5 Reimbursible O&M
|  | Unit | Unit Cost | Quantity | Amount
1 | Per diem allowances | Day | 3000 | 100 | 300000
2 | Travel expenses | Trip | 500 | 180 | 90000
3 | Communication costs | minute | 3 | 5000 | 15000
4 | Drafting, reproduction of reports | pages | 15 | 2000 | 30000
6 | Use of computers and other equipment | lumpsum |  |  | 300000
735000
|  |  |  | HR | 40750000 |  | 8935000
|  |  |  | Reimbursible | 6540200
|  |  |  | Sub total | 47290200 | 9458040
|  |  |  | Vat @ 5% | 2364510
Tax @ 5%
49654710

## Training
| Days | Nos | Honourium | Lunch | Total | Training Materials | Training bag | Stationery
system user training | 1 | 100 | 1000 | 500 | 150000 | 1000 | 1500 | 200 | 270000
System Admin training | 10 | 5 | 1000 | 500 | 75000 | 1000 | 1500 | 200 | 13500
[5 empty] | 225000 |  |  |  | 283500

## QCBS
Facts | Technical | 85%
| Financial | 15%
| Financial lowest | 30000000
Business Automation | Technical |  | 0
| Financial Cost |  | #DIV/0! | 0
#DIV/0!
Total Score
REVE | Technical |  | 0
| Financial Cost |  | #DIV/0!
|  | Total Score | #DIV/0!
Devnet | Technical |  | 0
| Financial Cost | 59145000 | 7.6084
|  | Total Score | 7.6084
Technivista | Technical |  | 0
| Financial Cost |  | #DIV/0!
|  | Total Score | #DIV/0!
Leads | Technical |  | 0
| Financial Cost |  | #DIV/0!
|  | Total Score | #DIV/0!
Syntech | Technical |  | 0
| Financial Cost |  | #DIV/0!
|  | Total Score | #DIV/0!